## $2M or more
Year | Agency Name | Project | Construction Method | Budget | Actual | Timeline | Actual | Comments
2022 | Alexandria City Public Schools |  | Design-Bid-Build | 2892847 | 2920000 | 300 | 450
2022 | Arlington County Government |  | Design-Bid-Build | 6080941 | 5945562 | 270 | 722 | N/A
2022 | Blue Ridge Resource Authority | Phase 1 Closure | Design-Bid-Build | 2946328 | 3342981 | 240 | 361 | This project was started and then stopped due to issues with the contractor chosen to perform the work. The amount paid out to this contractor totaled $744,258, which included a settlement of $416,213. Initial engineering costs were estimated to be $128,916. It was then rebid and another contractor was chosen to complete the project. The actual construction costs reported are for the rebid only ! That figure does not include first bid costs.
2022 | Bristol Virginia Utilities Authority | Basin Area 1107 Sewer Replacement Phase 1 | Design-Bid-Build | 3272209 | 3448216 | 210 | 464
2022 | Capital Region Airport Commission | Cargo Apron Eastside | Design-Bid-Build | 10500000 | 8838853 | 270 | 270 | none
2022 | Capital Region Airport Commission | East Side Apron Expansion | Design-Bid-Build | 4000000 | 2147881 | 150 | 150 | none
2022 | Charlottesville City | INVITATION FOR BID # CIRCUIT COURTHOUSE RENOVATION & ADDITION/18-26 | Design-Bid-Build | 5332994 | 4113326 | 403 | 1029 | Very slow performance of contractor in remedying punchlist items. Plumbing issues which required corrective action. Electrical issues (lighting) which required corrective action.
2022 | Chesapeake Bay Bridge and Tunnel District | Mill and Repave Trestles, Replace End Dams | Design-Bid-Build | 27000000 | 26721706 | 343 | 724 | No
2022 | Chesterfield County | River City Sportsplex Restroom Concessions | Design-Bid-Build | 4683700 | 4391701 | 180 | 230 | No
2022 | Chesterfield County | Fire Station #25 | Design-Bid-Build | 6149804 | 6410057 | 495 | 510 | Yes
2022 | Chesterfield County | Johnson Creek Sewer and Water Line | Design-Bid-Build | 4400000 | 4400000 | 300 | 325 | No
2022 | Chesterfield County Public Schools | Manchester Middle School Construction | Design-Bid-Build | 41283593 | 41283593 | 857 | 857
2022 | Chesterfield County Public Schools | Crestwood Elementary School Construction | Design-Bid-Build | 24178807 | 24219539 | 660 | 660
2022 | Chesterfield County Public Schools | Matoaca Elementary School Construction | Design-Bid-Build | 24861832 | 25140543 | 477 | 478
2022 | Chesterfield County Public Schools | Matoaca Middle School Addition | Design-Bid-Build | 10786253 | 10583541 | 385 | 377
2022 | City of Fairfax | Chain Bridge Road Sidewalk | Design-Bid-Build | 4467755 | 5062734 | 365 | 730
2022 | City of Harrisonburg | Project #256.2B Eastern City Limits to Port Republic Road (City Contract 2019019-PU-B) | Design-Bid-Build | 5000000 | 2522128 | 560 | 820 | None reported in the procurement file ITB 2019019-PU-B Notice to Proceed: 09/16/2019 Completion Date: 12/08/21 Final Payment Amount: $2,522,127.56
2022 | City of Newport News | Oak Avenue Sanitary Sewer Rehabilitation 23rd Street to 18th St, Section One | Other | 2037090 | 2483130 | 548 | 522
2022 | City of Newport News | Main Street Drainage Improvements | Other | 3428625 | 3946439 | 374 | 220
2022 | City of Newport News | Parking Garage, City Center, Phase Four | Other | 21593000 | 22531879 | 503 | 595
2022 | City of Staunton | STAUNTON HIGH School additions and renovations | Design-Bid-Build | 43130335 | 44041818 | 639 | 640 | MAIN AND AUX gym flooring issues to be resolved
2022 | City of Virginia Beach | BioPark Phase I | Design-Bid-Build | 3734928 | 3734869 | 180 | 342 | N/A
2022 | City of Virginia Beach | North Lake Holly Section IIIA | Design-Bid-Build | 25351135 | 27874216 | 548 | 711 | N/A
2022 | City of Virginia Beach | Sherwood Lakes Drainage Impr. | Design-Bid-Build | 3400000 | 3132290 | 270 | 337 | N/A
2022 | City of Virginia Beach | South Lake Holly Section IV | Design-Bid-Build | 16009587 | 15681839 | 913 | 1066 | N/A
2022 | City of Virginia Beach | Police 4th Precinct Bldg | Design-Bid-Build | 9051779 | 7103996 | 405 | 624 | N/A
2022 | City of Virginia Beach | Central Plant Generator Bldg | Design-Bid-Build | 4975585 | 4910716 | 300 | 723 | N/A
2022 | City of Virginia Beach | Royal Palm Arch Sanitary Sewer Rehab | Design-Bid-Build | 5300000 | 5536819 | 450 | 582 | N/A
2022 | City of Williamsburg | Monticello Ave PPTA | Design-Build | 5000000 | 3850113 | 334 | 632 | Long Completion date was due to material availability, weather along with Covid19 delays.
2022 | City of Winchester | Handley Library Improvements | Design-Bid-Build | 2600000 | 2578857 | 300 | 480
2022 | City of Winchester | Trails at the Museum of the Shenandoah Valley | Design-Bid-Build | 2800000 | 2605666 | 270 | 480
2022 | City of Winchester | Water Meter Replacements | Design-Bid-Build | 4000000 | 3588297 | 365 | 270
2022 | City of Winchester | Water Storage Tank Replacement | Design-Bid-Build | 3500000 | 39737 | 270 | 450
2022 | County of Fairfax | Scotts Run at Old Meadow Road Park | Design-Bid-Build | 2214820 | 2337048 | 390 | 457 | NA
2022 | County of Fairfax | Massey Demo | Design-Bid-Build | 18682000 | 6941108 | 615 | 689 | NA
2022 | County of Fairfax | Crisis Care | Design-Bid-Build | 2700000 | 2646000 | 352 | 387 | NA
2022 | County of Fairfax | Woodlawn Fire Station | Design-Bid-Build | 9933000 | 9492613 | 644 | 531 | NA
2022 | County of Fairfax | Edsall Road Fire Station Temp | Design-Bid-Build | 2743981 | 2306134 | 198 | 378 | NA
2022 | County of Fairfax | Murraygate Village Apartments | Design-Bid-Build | 11973575 | 15440928 | 571 | 749 | NA
2022 | County of Loudoun | Construction of the Public Safety Firing Range | Design-Bid-Build | 20398000 | 21360506 | 460 | 658 | none
2022 | County of Loudoun | Construction of the Lovettesville Community Center | Design-Bid-Build | 10808400 | 1283305 | 912 | 193 | Terminated for convenience after phase 1 completed
2022 | County of Loudoun | Leesburg Fire and Rescue Station 20 Expansion | Design-Bid-Build | 4263000 | 4790258 | 456 | 613 | none
2022 | County of Loudoun | Construction of the New Loudoun County Animal Services Facility | Design-Bid-Build | 17975850 | 18311445 | 540 | 791 | none
2022 | County of Loudoun | Potomac Green Park Improvement | Design-Bid-Build | 3275000 | 3413886 | 240 | 321 | NONE
2022 | County of Loudoun | Construction of the DC United Training Site | Design-Bid-Build | 3612858 | 3747373 | 180 | 180 | Post Construction Issue with Storm Water Basin which was resolved with Shirley Contracting at no additional cost to the County.
2022 | County of Loudoun | Construction of the Leachate Pump Station | Design-Bid-Build | 2586790 | 2807159 | 450 | 540 | none
2022 | County of Loudoun | Construction of CCD Unit Cell A1 Bottom Liner System for SWMF | Design-Bid-Build | 4596000 | 4738025 | 244 | 307 | NONE
2022 | Department of Military Affairs | DSCR State Headquarters Administrative Conversion Restoration/Repair | Design-Bid-Build | 3000000 | 3025855 | 365 | 436
2022 | Fairfax County Schools | McLean High School Modular | Design-Bid-Build | 1948400 | 2312765 | 182 | 547 | NA
2022 | Fairfax County Schools | Belle View Elementary School Renovation | Design-Bid-Build | 20790000 | 20957526 | 791 | 1156 | NA
2022 | Fairfax County Schools | Silverbrook Elementary School Renovation | Design-Bid-Build | 19994000 | 20032321 | 615 | 980 | NA
2022 | Fairfax County Schools | Mount Vernon Woods Elementary School Renovation | Design-Bid-Build | 16750000 | 17044085 | 851 | 1216 | NA
2022 | Frederick County | Crossover Blvd | Design-Bid-Build | 17593 | 16886121 | 27 | 27 | no issues; completed on time and under budget
2022 | Frederick County Public Schools | 12th Elementary School Construction | Design-Bid-Build | 28500000 | 27227401 | 731 | 520 | commissioning issues on lighting
2022 | Frederick County Sanitation Authority | Orchardview Well- Water Expansion | Design-Bid-Build | 4772750 | 4925464 | 210 | 326 | There are no post project issues
2022 | Galax City Public Schools | Galax Elementary School Renovation Project | Design-Bid-Build | 15552000 | 1710000 | 973 | 1187 | None
2022 | Hampton Roads Sanitation District | Pump Station Generator & Stand- By Pump Upgrades | Design-Bid-Build | 3823000 | 3887792 | 485 | 524 | None
2022 | Hampton Roads Sanitation District | Pressure Reducing Station Reliability Upgrades | CM@Risk | 33282000 | 30454524 | 1135 | 1135 | None
2022 | Hampton Roads Sanitation District | Deep Creek Interceptor Force Main | Design-Bid-Build | 4388122 | 4967945 | 320 | 358 | None
2022 | Hampton Roads Sanitation District | Providence Road Offline Storage Facility | Design-Build | 29953000 | 31131582 | 855 | 881 | None
2022 | Hampton Roads Sanitation District | Boat Harbor Treatment Plant Switchgear & Controls | Design-Bid-Build | 6893065 | 6821171 | 580 | 580 | None
2022 | Hampton Roads Sanitation District | Mathews Main Vacuum Pump Station Replacement | Design-Bid-Build | 2251210 | 2454272 | 330 | 561 | None
2022 | Hampton Roads Sanitation District | Williamsburg Treatment Plant Generator & Switchgear Replacement | Design-Bid-Build | 13992672 | 14115477 | 690 | 698 | None
2022 | Hampton Roads Sanitation District | Jefferson Avenue Extension Gravity Improvements | Design-Bid-Build | 2248120 | 2088603 | 270 | 274 | Extended warranty on certain items.
2022 | Hampton Roads Sanitation District | Huxley to Middle Ground Blvd IFM | Design-Bid-Build | 3943409 | 4115878 | 480 | 584 | Warranty repair effort underway on valve.
2022 | Hampton Roads Sanitation District | Manhole & Siphon Rehab - North Shore System | Design-Bid-Build | 7260921 | 6905511 | 490 | 760 | Extended warranty on certain items.
2022 | Hampton Roads Sanitation District | Nansemond Treatment Plant Land Stabilization & Improvements | Design-Bid-Build | 3091750 | 3210270 | 365 | 365 | Warranty item to replace trees still unresolved.
2022 | Hanover County | Sliding Hill road | Design-Build | 7000000 | 6836855 | 487 | 438
2022 | Hanover County | Atlee High School HVAC | Design-Build | 3500000 | 3984558 | 76 | 76
2022 | Harrisonburg- Rockingham Regional Sewer Authority | Blacks Run Interceptor Improvements | Design-Bid-Build | 8210000 | 6537674 | 550 | 469
2022 | Henrico County Government | Dorey Park Baseball Field Improvements | Design-Bid-Build | 3320748 | 3320748 | 330 | 372 | NONE
2022 | Henrico County Government | Woodman Road Roundabout | Design-Bid-Build | 3561238 | 4409428 | 540 | 580 | NONE
2022 | Henrico County Government | Montrose Terrace Area Sewer and Water Rehabilitation | Design-Bid-Build | 2607267 | 2757043 | 360 | 405 | NONE
2022 | Henry County | Philpott Water Filtration Plant Upgrade to 6.0 MGD | Design-Bid-Build | 13626557 | 13626557 | 730 | 1095 | One of the raw water pumps and finished water pumps having issues.
2022 | James Madison University | New Construction Convocation Hall | CM@Risk | 113900000 | 115675841 | 938 | 907
2022 | James Madison University | Jackson Hall Renovation | Design-Bid-Build | 5497000 | 6164000 | 407 | 408 | Covid; building wasn't able to be fully occupied until almost summer of 2021.
2022 | James Madison University | Construct New College of Business | CM@Risk | 70822168 | 72641206 | 1106 | 1078
2022 | Longwood University | New Academic Building | Design-Bid-Build | 16115400 | 16530511 | 630 | 1425 | Non
2022 | Loudoun County Public Schools | Lightridge High Schools (HS-9) new construction | Design-Bid-Build | 110399300 | 114043778 | 699 | 973 | None
2022 | Loudoun County Public Schools | Tuscarora High School Entry Modification and Renovation (GMP 3 under CMaR contract 19-476) | CM@Risk | 4403103 | 4403106 | 699 | 973 | None
2022 | Loudoun County Public Schools | Entry Modifications for 24 ES and MS (group 2a and 2B- (GMP 2 under CMaR contract 18-474) | CM@Risk | 6713879 | 4008476 | 334 | 516 | None
2022 | Nelson County | Nelson Memorial Library Expansion & Renovation | Design-Bid-Build | 2337424 | 2448834 | 365 | 461
2022 | NRV Regional Water Authority | Plum Creek Transmission Main Phase 1 and Phase 2 | Design-Bid-Build | 9168000 | 9892500 | 595 | 585 | None
2022 | Old Dominion University | Improvements:Convert Gymnasium into a Competition Women's Volleyball Facility | Design-Bid-Build | 2788000 | 2910708 | 448 | 502 | None
2022 | Prince William County | Construction of Fire and Rescue Station 22 | Design-Bid-Build | 16970713 | 16766731 | 112020 | 42022 | Occupancy December 2020, Project Closeout Completed April 2022
2022 | Prince William County Schools | Potomac Shores Middle School | Design-Bid-Build | 54104420 | 52542298 | 867 | 929 | None
2022 | Richmond Metropolitan Transportation Authority | Miscellaneous Repairs 2020 | Design-Bid-Build | 2691923 | 2109176 | 365 | 426 | None
2022 | Shenandoah County | Phase IV Landfill Cell | Design-Bid-Build | 3025000 | 2864373 | 7302021 | 8312021 | n/a
2022 | Spotsylvania County | Animal Shelter Expansion, Renovation | Other | 7002486 | 7069945 | 780 | 977 | none
2022 | Stafford County Public Schools | Energy Performance Contract for Stafford County Public Schools | Other | 10650651 | 10650651 | 995 | 1025
2022 | University of Mary Washington | Renovate Residence Halls - Phase II (Virginia Hall) | CM@Risk | 17901616 | 19041679 | 343 | 357
2022 | University of Virginia | University Hall (U- Hall) Abatement & Demolition | Design-Build | 9800000 | 6518658 | 289 | 1010 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2022 | University of Virginia | Carr's Hill Renovation | CM@Risk | 11700000 | 1036433 | 537 | 1393 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2022 | University of Virginia | Athletics Complex Phase 1 Early Site Package | Design-Bid-Build | 8400000 | 11871111 | 242 | 847 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2022 | University of Virginia | East Range Stormwater Improvement | Design-Bid-Build | 2300000 | 2664165 | 248 | 1393 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2022 | University of Virginia | North Chiller Plant Switchgear Replacement | Design-Bid-Build | 2800000 | 3221399 | 302 | 721 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2022 | University of Virginia | Memorial to Enslaved Laborers | Design-Bid-Build | 4000000 | 54889873 | 348 | 1278 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2022 | University of Virginia | New Softball Stadium | CM@Risk | 13000000 | 19641061 | 528 | 1409 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2022 | University of Virginia | UH Fire Alarm Notification Upgrade PH 1 & Sprinkler Ph 1 | Other | 3348302 | 3348302 | 554 | 855 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center - A246 College at Wise. This report is for A209 Medical Center
2022 | University of Virginia | ECCCC 4th Floor Fit Out | CM@Risk | 7950000 | 10488253 | 780 | 1647 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center - A246 College at Wise. This report is for A209 Medical Center
2022 | University of Virginia | 652 Peter Jefferson Parkway, 2nd Floor Renovation - Breast Care Center | Design-Bid-Build | 7000000 | 4284848 | 301 | 997 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center - A246 College at Wise. This report is for A209 Medical Center
2022 | University of Virginia | Southwest Virginia Higher Education Center Service Corridor - Storage Addition Generator Replacement | Design-Bid-Build | 2360000 | 2097130 | 266 | 899 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center - A246 College at Wise. This report is for A246 College at Wise.
2022 | Virginia Polytechnic Institute and State University | Student Athlete Performance Center | Design-Bid-Build | 17059490 | 16763923 | 487 | 487
2022 | Virginia Port Authority | Dredging IFB - Public Opening | Design-Bid-Build | 10190110 | 9534520 | 532 | 532 | Sealed Competitive Bidding via an IFB
2022 | Warren County Public Schools | AS Rhodes Elementary School | Design-Bid-Build | 3096300 | 4807918 | 185 | 221
2022 | Washington County Service Authority | Galvanized Waterline Replacement Project Phase 3 Division 1 | Design-Bid-Build | 4522426 | 4322915 | 365 | 244 | N/A
2022 | Washington County Service Authority | Galvanized Waterline Replacement Project Phase 3 Division 2 | Design-Bid-Build | 2179520 | 2074997 | 365 | 320 | N/A
2022 | Western Virginia Water Authority | Airport Road to Palm Valley Road SS Replacement | Design-Bid-Build | 2233042 | 2244405 | 270 | 306 | None
2022 | Western Virginia Water Authority | Crystal Spring Pump Relocation | Design-Bid-Build | 4931027 | 4771046 | 300 | 339 | None
2021 | Albemarle County | Hollymead Dam Spillway Improvement | Design-Bid-Build | 6910200 | 6927836 | 571 | 1407
2021 | Arlington County Government | Washington Boulevard Bike Trail Phase II | Design-Bid-Build | 2535251 | 2140307 | 365 | 221 | N/A
2021 | Arlington County Government | Head Start Project | Design-Bid-Build | 3680000 | 4130000 | 190 | 379 | N/A
2021 | Arlington County Government | Neighborhood Conservation Streetscape Infrastructure Projects (N554, N551, N527) | Design-Bid-Build | 2415808 | 2383000 | 510 | 540 | N/A
2021 | Arlington Public Schools | Randolph Elementary School HVAC Improvement Project | Design-Bid-Build | 6200000 | 5136445 | 441 | 468 | Construction commenced June 22, 2018. Warranty period expired October 3, 2020. The budget information provided for the two projects includes both construction costs and soft costs.
2021 | Arlington Public Schools | Gunston Middle School HVAC Improvement Project | Design-Bid-Build | 10655000 | 8723689 | 442 | 467 | Construction commenced June 21, 2018. Warranty period expired October 15, 2020. The budget information provided for the two projects includes both construction costs and soft costs.
2021 | Charlottesville City | EMMET-IVY WATER MAIN REPLACEMENT | CM@Risk | 1995140 | 2329944 | 210 | 384 | Procurement Method for line item 1 was an IFB.
2021 | Chesterfield County | Robious Road Widening – Powhatan County Line to Robious Forest Way | Design-Bid-Build | 5175000 | 4635711 | 204 | 371 | None
2021 | Chesterfield County Public Schools | Construction, Falling Creek Middle School Improvements | Design-Bid-Build | 5959801 | 3450457 | 118 | 420 | None
2021 | City of Chesapeake | Centerville Rehabilitation | Design-Bid-Build | 7793596 | 7911739 | 9 | 9 | NONE
2021 | City of Colonial Heights | Dupuy Avenue Street Improvements | Design-Bid-Build | 3575140 | 3528546 | 8 | 11 | Manholes were not to grade, Documentation for buy America and water meters box lids, Sewer line clean nout collars not to 6" depth This project was a Sealed Bid.
2021 | City of Harrisonburg | I-81 Exit 245 NB Off-Ramp Realignment (City Contract 2020006- PW-B) | Design-Bid-Build | 3000000 | 2667664 | 9 | 9 | Procurement Method: ITB (2020006-PW-B) Projected Timeline: Completed by 9/18/2020 (9 Months) Actual Completion Time: Completed on 9/18/2020 (9 Months), Final Payment Made 9/30/2020
2021 | City of Lynchburg | Indian Hill Road Bridge over Ivy Creek | Design-Bid-Build | 2028719 | 2012748 | 270 | 240 | NONE
2021 | City of Newport News | SCOT Center PPEA | CM@Risk | 38811692 | 39348167 | 412 | 576 | Project indicated as Other were issued as Invitation for Bids.
2021 | City of Newport News | Residential Roadway Resurfacing | Other | 1762000 | 2845560 | 306 | 480 | Project indicated as Other were issued as Invitation for Bids.
2021 | City of Newport News | Huntington Avenue Bridge | Other | 2134586 | 2222817 | 266 | 458 | Project indicated as Other were issued as Invitation for Bids.
2021 | City of Newport News | Lee Hall Water Reclamation | Other | 2000000 | 2024365 | 281 | 537 | Project indicated as Other were issued as Invitation for Bids.
2021 | City of Norfolk | Wards Corner Pump Station No. 150 Water & Sewer Improvements, Phase V | Design-Bid-Build | 3332819 | 3968445 | 829 | 849 | None
2021 | City of Norfolk | Pump Station No. 17 Service Area Water & Sewer Replacement 10 | Design-Bid-Build | 2396749 | 2139064 | 698 | 519 | None
2021 | City of Norfolk | Pump Station No. 23, Phase 7 Water & Sewer Replacement | Design-Bid-Build | 2354595 | 2354595 | 681 | 691 | None
2021 | City of Norfolk | East Ocean View Pump Station No. 88 Water & Sewer Improvements, Phase V | Design-Bid-Build | 2249886 | 1827299 | 527 | 537 | None
2021 | City of Virginia Beach | Central Plant Generator Building | Design-Bid-Build | 2300000 | 2754070 | 300 | 279 | Project closeout issues
2021 | City of Virginia Beach | Indian River Road & Kempsville Road Intersection Improvements | Design-Bid-Build | 8337746 | 11022818 | 640 | 575
2021 | City of Virginia Beach | South Lake Holly Watershed Improvements | Design-Bid-Build | 10260485 | 9039817 | 913 | 1066
2021 | City of Virginia Beach | Virginia Beach Sports Center | Other | 65804076 | 65365758 | 863 | 820
2021 | City of Williamsburg | Monticello Ave PPTA | Design-Build | 3850144 | 3531954 | 610 | 912 | Covid-related - signal poles delay, weather condition delay
2021 | City of Winchester | Handley Library Improvements | Other | 2600000 | 2578857 | 300 | 480 | None
2021 | City of Winchester | Trails at the Museum of the Shenandoah Valley | Other | 2800000 | 2605666 | 270 | 480 | none
2021 | City of Winchester | Water Meter Replacements | Other | 4000000 | 3588297 | 365 | 270 | none
2021 | City of Winchester | Water Storage Tank Replacement | Other | 3500000 | 3973792 | 270 | 450 | none
2021 | County of Fairfax | Bailey's Shelter & Supportive Housing | Design-Bid-Build | 8843000 | 9272447 | 518 | 599
2021 | County of Fairfax | DVS Facilities Upgrades West Ox Facility | Design-Bid-Build | 4020000 | 4597804 | 545 | 660
2021 | County of Fairfax | Reston Temporary Fire Station | Design-Bid-Build | 2479000 | 2820966 | 210 | 340
2021 | County of Fairfax | Reston Community Center Aquatics Facility | Design-Bid-Build | 4539000 | 4651642 | 305 | 315
2021 | County of Fairfax | Court Rooms, Phase II A&B | Design-Bid-Build | 2463000 | 2525233 | 345 | 425
2021 | County of Fairfax | Hayfield Road Pipe Conveyance System | Design-Bid-Build | 6956900 | 7146984 | 420 | 355
2021 | County of Fairfax | Hunting Creek @ Fairchild | Design-Bid-Build | 1911007 | 2116875 | 420 | 318
2021 | County of Fairfax | Old Courthouse Spring Branch Valley Park | Design-Bid-Build | 5886798 | 6140875 | 450 | 459
2021 | County of Fairfax | Solids Processing Rehabilitation, Phase II | Design-Bid-Build | 16750000 | 18433980 | 915 | 844
2021 | County of Loudoun | Interior Construction of 742 Miller Drive | Design-Bid-Build | 2099000 | 2158453 | 120 | 165 | None
2021 | County of Loudoun | 751 Miller Drive Interior Buildout | Design-Bid-Build | 2850084 | 2885443 | 120 | 180 | None
2021 | County of Loudoun | Construction of the DC United Training Site | Design-Bid-Build | 3747372 | 3688754 | 150 | 195 | None
2021 | County of York | CONSTRUCTION OF FIRE STATION #1 (GRAFTON AREA) | Design-Bid-Build | 6197980 | 6636484 | 395 | 513 | DRAINAGE IMPROVEMENT PROJECT (IFB Y-10157-FS), AWARDED TO WALTER C VIA. FOR $26,900.00 THE PROCUREMENT METHOD FOR THE CONSTRUCTION OF FIRE STATION #1 WAS DONE THROUGH AN INVITATION FOR BIDS (IFB# 2075 - WHICH WAS POSTED ON EVA ON 1/3/2018)
2021 | Department of Military Affairs | Renovate & Convert DSCR - Warehouse | Design-Bid-Build | 3761000 | 3512271 | 315 | 336 | Decorative signage delivery delays after substantial completion
2021 | Department of Military Affairs | Training Aids Support Center - Fort Pickett | Design-Bid-Build | 4207000 | 4154814 | 365 | 536 | Geothermal system will not maintain pressure
2021 | Greene County Public Schools | L618GCPS - DEB_CCP_William Monroe Middle and High School Rennovation | CM@Risk | 23975800 | 24489225 | 532 | 868 | Slope issues on the loading dock at the Middle School. Repaired by contractor. Drain line issues at the MS causing back up in cafeteria and restrooms. Had to pull up a section of terrazzo and slab to repair.
2021 | Greensville County | Otterdam Road Phase II | Design-Bid-Build | 2203902 | 2164577 | 285 | 273 | n/a
2021 | Henrico County Government | Meredith Branch Force Main | Design-Bid-Build | 8500000 | 706382 | 730 | 1308 | Late completion
2021 | Henrico County Government | Chamberlayne Farms and Chamberlayne Hills Area Sanitary Sewer Rehabilitation (SH- 53) | Design-Bid-Build | 4935015 | 4935015 | 670 | 769 | n/a
2021 | Henrico County Government | Enterprise Parkway & Broad Street Area (SH-15 Part 1, Phase 1) Sewer Rehabilitation | Design-Bid-Build | 2775200 | 3362284 | 330 | 553 | n/a
2021 | Henrico County Government | High School Athletic Field Improvements - Phase 3 (Deep Run, Glen Allen, and Godwin High Schools) | Design-Bid-Build | 7500000 | 7263059 | 250 | 300 | n/a
2021 | Henrico County Government | Henrico County Police Annex Building | Design-Bid-Build | 3065000 | 3172316 | 395 | 395 | n/a
2021 | Loudoun County Public Schools | Security Vestibule and Associated Renovations | CM@Risk | 4465155 | 5210141 | 15 | 16 | Punchlist and scope completion after occupancy - contractor compliance with contract in regards to proper documentation - COVID pandemic
2021 | Old Dominion University | New Construction - Campus Dining Improvements - Webb University Center | Design-Bid-Build | 2494000 | 3130057 | 305 | 670 | The 670 calendar days cover the 1-Year Warranty Period.
2021 | Prince Edward County | STEPS Center - Renovation | Design-Bid-Build | 2778541 | 2327264 | 365 | 732
2021 | Prince Edward County | DSS Building - Construction | Design-Bid-Build | 4018086 | 3891973 | 365 | 735
2021 | Prince Edward County | Courthouse - Renovation | Design-Bid-Build | 4518016 | 4796681 | 365 | 741
2021 | Radford University | Renovate Curie and Reed Halls | CM@Risk | 22708530 | 22706892 | 602 | 1080
2021 | Roanoke City Government | E911 VA 811 Facility | Other | 10741087 | 11160233 |  |  | None provided
2021 | Roanoke City Government | Fire Station 7 Memorial | Other | 5570000 | 6021345 | 420 | 545 | None provided
2021 | Rockingham County | Port Road Emergency Response Station | Design-Bid-Build | 5277000 | 5396912 | 18 | 18 | None
2021 | Rockingham County Public Schools | John C. Myers Elementary School | Other | 14110630 | 13610153 | 536 | 596
2021 | Shenandoah County | Sheriff's Office | Design-Bid-Build | 8500000 | 9678345 | 7302020 | 11302020 | n/a
2021 | University of Mary Washington | Improvements - Renovate Residence Halls (Willard Hall Renovation) | CM@Risk | 18400780 | 19311522 | 286 | 376
2021 | University of Virginia | Main Heating Plant Boiler #6 | CM@Risk | 6400000 | 7285505 | 670 | 837 | Approved - also confirmed by Martin West and Jenn Glassman here at UVA
2021 | Virginia Polytechnic Institute and State University | Athletic Weight Room | Design-Bid-Build | 3490000 | 3437991 | 180 | 180 | none
2021 | Virginia Polytechnic Institute and State University | Student Athlete Performance Center | Design-Bid-Build | 17059490 | 16763923 | 450 | 450 | none
2021 | Virginia State University | WHITING HALL HVAC REPLACEMENT | Design-Bid-Build | 2199000 | 2382243 | 120 | 137 | Service area constraints and operations and maintenance training of staff; compressor failures
2021 | Western Virginia Water Authority | Muse Spring Water Treatment Plant | Design-Bid-Build | 3385526 | 3665110 | 300 | 688 | none
2021 | Western Virginia Water Authority | Summit View Sewer | Design-Bid-Build | 5207217 | 3758862 | 210 | 336 | none
2020 | Arlington County | South Clark Demolition and Traffic Signal Project | Other | 4499320 | 4699750 | 176 | 534
2020 | Arlington County | Chiller Plant replacement | Other | 3685275 | 3360192 | 457 | 488
2020 | Arlington County | Clarendon circle government | Other | 2112200 | 2299973 | 365 | 635 | Post-Project issues with utilities and as-builts
2020 | Arlington County | Madison Manor Park | Other | 2820615 | 2586569 | 320 | 404
2020 | Charlottesville City | Sanitary storm sewer | Design-Bid-Build | 4397808 | 4493982 | 730 | 730 | Procurement Method: Invitation for Bid This project (term contract) being reported had a duration of 2 fiscal years, 2018-2019 and 2019-2020.
2020 | Chesterfield County | Fuel farm replacement | Design-Bid-Build | 2900000 | 2343951 | 180 | 357 | THIS PROJECT WAS DONE AS AN INVITATION FOR BID (IFB)
2020 | Chesterfield County | Improvement at Falling Creek Middle School | Design-Bid-Build | 2300000 | 3450457 | 118 | 296 | issue over a damaged Air Handling Unit in the cafeteria/kitchen during the project and likely extended completion time
2020 | City of Chesapeake | Sunray Overpass Rehab | Design-Bid-Build | 3200000 | 2776518 | 410 | 407 | Procurement Method : Other -- Invitation for Bids (IFB)
2020 | City of Chesapeake | Centerville Turnpike Bridge Rehab | Design-Bid-Build | 8100000 | 7992721 | 515 | 508 | Procurement Method : Other -- Invitation for Bids (IFB)
2020 | City of Fairfax | Police Firing Range | Other | 3999000 | 4449482 | 365 | 511
2020 | City of Fairfax | Northfax Intersection & Drainage Improvement Project | Other | 23848500 | 23848500 | 730 | 730 | Traffic signal was damaged in vehicular accident before punch list was completed.
2020 | City of Hampton | Salt Ponds Inlet Improvement | Other | 2381286 | 3002203 | 240 | 236
2020 | City of Harrisonburg | Grace St Extension Project | Design-Bid-Build | 3000926 | 2968383 | 272 | 272 | None
2020 | City of Lynchburg | MAIN STREET BRIDGE | Design-Bid-Build | 7131385 | 7008357 | 450 | 540 | NONE
2020 | City of Lynchburg | WWTP OPERATIONS BUILDING RENOVATION | Design-Bid-Build | 3504328 | 3504328 | 605 | 765 | NONE
2020 | City of Lynchburg | 5TH STREET UTILITY REPLACEMENT - PHASE III | Design-Bid-Build | 4652668 | 4297198 | 434 | 487 | NONE
2020 | City of Lynchburg | LIBERTY MOUNTAIN DR - PHASE III | Design-Bid-Build | 4158018 | 4158018 | 430 | 460 | NONE
2020 | City of Lynchburg | DENVER/YANCEY UTILITY REPLACEMENT | Design-Bid-Build | 2532178 | 2532178 | 365 | 259 | NONE
2020 | City of Newport News | 2019 Residential Resurfacing and Concrete Program | Design-Bid-Build | 1416317 | 2677703 | 240 | 390
2020 | City of Newport News | UPC #107271 Patrick Henry Drive Extended | Design-Bid-Build | 3202814 | 3410617 | 564 | 563
2020 | City of Norfolk | Pump Station 17 Service Area was replacement - PH 10 | Other | 2330221 | 2139064 | 360 | 285 | N/A
2020 | City of Suffolk | Rosewood/Old Sumerton Water Main Extension Project | Design-Bid-Build | 2615044 | 2541442 | 348 | 370 | None
2020 | City of Virginia Beach | Northgate Ditch Improvements | Design-Bid-Build | 1878000 | 2035079 | 240 | 731
2020 | City of Virginia Beach | North Lake Holly Watershed Improvements | Design-Bid-Build | 5814176 | 4612895 | 548 | 715
2020 | City of Winchester | Woodstock Lane Infrastructure Improvements | Other | 6200000 | 6035963 | 365 | 365
2020 | County of Fairfax | Flatlick Branch Phase III Stream Restoration | Design-Bid-Build | 2068420 | 2314440 | 435 | 375 | NA
2020 | County of Fairfax | Pike Branch Tributary at Ridgeview Park | Design-Bid-Build | 2804150 | 2392893 | 425 | 468 | NA
2020 | County of Fairfax | Difficult Run Tributary at Brittenford Stream Restoration | Design-Bid-Build | 3155064 | 3398232 | 450 | 433 | NA
2020 | County of Fairfax | Lee Chapel Road Walkway | Design-Bid-Build | 2276700 | 2311156 | 240 | 241 | NA
2020 | County of Fairfax | Reston Community Center Aquatics | Design-Bid-Build | 5922000 | 5481320 | 305 | 315 | NA
2020 | County of Fairfax | Reston Temporary Fire Station | Design-Bid-Build | 3320000 | 3304003 | 210 | 340 | NA
2020 | County of Fairfax | DVS – West Ox Facility | Design-Bid-Build | 5109756 | 5538471 | 545 | 660 | NA
2020 | County of Fairfax | Herndon Station Existing Garage Repairs | Design-Bid-Build | 800000 | 2606075 | 180 | 241 | NA
2020 | County of Fairfax | Innovation Center Station Parking Garage | Design-Bid-Build | 51639920 | 49512692 | 700 | 850 | NA
2020 | County of Loudoun | Construction of the DC United Stadium Site | Design-Bid-Build | 5573333 | 7626449 | 473 | 548 | Warranty issues related to landscaping and a delay in a bus shelter drip edge. However, all issues have been resolved.
2020 | County of Loudoun | Interior Construction 742 Miller Drive | Design-Bid-Build | 2099000 | 2158453 | 255 | 255 | None
2020 | County of Loudoun | 751 Miller Drive Interior Buildout | Design-Bid-Build | 2850084 | 3140354 | 182 | 182 | None
2020 | County of York | HVAC REPLACEMENT, METAL ROOF & EXTERIOR WINDOWS AND DOORS | Design-Bid-Build | 6804231 | 7254875 | 548 | 820
2020 | County of York | CONSTRUCTION, FIRE STATION | Design-Bid-Build | 6500000 | 6636484 | 441 | 539
2020 | Department of Military Affairs | Renovate & Convert DSCR - Warehouse | Design-Bid-Build | 3418000 | 3512271 | 315 | 336
2020 | Department of Military Affairs | Construct Ft Pickett Training Aids Center | Design-Bid-Build | 4161000 | 4154814 | 365 | 536
2020 | Dickenson County | Social Services Offices | Design-Build | 2413051 | 2674812 | 221 | 221 | Included partial demolition of old school and renovation of remainder into office space
2020 | Eastern Virginia Medical School | Hofheimer Hall 4th & 5th Floors and Roof Renovations. | Design-Bid-Build | 3899066 | 3321071 | 390 | 470 | (1) Operation & Maintenance Manuals are still outstanding, (2) Quality issues with workmanship, (3) Contractor was late in substantial completion by approximately 10 weeks.
2020 | Frederick County Sanitation Authority | Stonewall Ballfields | Design-Bid-Build | 2027733 | 2181075 | 242 | 355 | There are no post project issues
2020 | Frederick County Sanitation Authority | Western Water Loop | Design-Bid-Build | 3934005 | 4656688 | 338 | 368 | There are no post project issues
2020 | Greensville County Water & Sewer Authority | Raw Water Intake Facility - Contract F | Design-Bid-Build | 3610000 | 3679698 | 395 | 640 | None
2020 | Greensville County Water & Sewer Authority | Raw Water Supply Project - Contract H | Design-Bid-Build | 2164992 | 2139741 | 390 | 626 | None
2020 | Halifax County Service Authority | Sutphin Road Sewer Interceptor | Design-Bid-Build | 3134505 | 3145000 | 395 | 410 | None
2020 | Halifax County Service Authority | Cowford Road WWTP Conversion | Design-Bid-Build | 3059034 | 2995700 | 720 | 790 | E & S due to season
2020 | Hampton Roads Sanitation District | Orcutt Ave & Mercury Blvd GS Improvements | Design-Bid-Build | 7763168 | 7600000 | 554 | 584 | None
2020 | Hampton Roads Sanitation District | Lucas Creek-Woodhaven IFM Replacement Phase I | Design-Bid-Build | 2655506 | 2622283 | 411 | 411 | None
2020 | Hanover County | Airport Hanger | Design-Bid-Build | 2400000 | 2323575 | 270 | 324 | None
2020 | Harrisonburg- Rockingham Regional Sewer Authority | Enhanced Biosolids Reuse and Reduction Project | Design-Bid-Build | 11222933 | 11320842 | 600 | 644 | None
2020 | Henrico County Government | Water Reclamation Facility Administration/Laboratory and Digester Complex HVAC Upgrade | Design-Bid-Build | 2390000 | 2474880 | 330 | 731 | None
2020 | Henrico County Government | Chamberlayne Elementary School Renovations | Design-Bid-Build | 10892301 | 8270524 | 738 | 858 | None
2020 | Henrico County Government | Glen Allen Elementary School Addition | Design-Bid-Build | 5010139 | 4875127 | 699 | 701 | None
2020 | Henrico County Government | Pemberton Elementary School Renovation | Design-Bid-Build | 10829171 | 10131210 | 699 | 824 | None
2020 | Henrico County Government | Crestview Elementary School Renovations | Design-Bid-Build | 9283941 | 8425497 | 484 | 736 | None
2020 | Henrico County Government | Tuckahoe Middle School Renovation | Design-Bid-Build | 22632393 | 27796552 | 700 | 777 | None
2020 | Henrico County Government | Fire Training Facility | Design-Bid-Build | 2902524 | 2778645 | 326 | 543 | None
2020 | Henrico County Government | High School Athletic Field Improvements – Phase 2 | Design-Bid-Build | 1953556 | 2143582 | 243 | 243 | None
2020 | Henry County | Commonwealth Crossing Business Centre 1 Million Gallon Elevated Water Tank Project | Design-Bid-Build | 2781000 | 2801827 | 451 | 591 | None
2020 | James Madison University | Wilson Hall Renovation | CM@Risk | 20008990 | 20186612 | 378 | 366
2020 | James Madison University | East Campus Student Housing | CM@Risk | 47850000 | 49503462 | 414 | 504 | Tremendous workmanship and system errors from Contractor.
2020 | James Madison University | East Campus Parking Deck | CM@Risk | 34676293 | 35369303 | 1039 | 521
2020 | James Madison University | Phillips Dining Hall | CM@Risk | 25112184 | 25826276 | 542 | 595 | Extensive Contractor delays and quality issues.
2020 | Longwood University | Construct Admissions Office | Design-Bid-Build | 8561000 | 7858846 | 450 | 614 | project closeout issues
2020 | Louisa County | Construction of Cell 2 and Related Infrastructure at the Louisa County Landfill | Design-Bid-Build | 2398827 | 2464059 | 451 | 453 | Computer control board for leach aid pump had an issue, but was resolved by contractor under warranty.
2020 | Montgomery County Public Schools | Christiansburg High School Athletic Fields Renovation | Other | 2915600 | 2799042 | 200 | 330 | Signage for fields was delayed due to COVID-19 issues.
2020 | New Kent County | New Kent County Fire Station #5 | Design-Build | 2825453 | 2961359 | 455 | 413 | No issues noted.
2020 | Old Dominion University | SB Ballard Stadium Renovations | CM@Risk | 53653240 | 5960724 | 445 | 445 | Warranty
2020 | Old Dominion University | Koch Hall HVAC/Roof Replacement | Design-Bid-Build | 2100000 | 2229354 | 367 | 307 | Warranty
2020 | Old Dominion University | WEBB Center Cafe' 1201 Renovations | Design-Bid-Build | 3300000 | 3130057 | 242 | 281 | None
2020 | Prince William County Service Authority | Sudley Rd 14-inch Replacement, Loop Closures and Realignment - Phase 1 | Other | 2326294 | 2326294 | 630 | 730
2020 | Prince William County Service Authority | Colchester Interceptor and Pump Station | Other | 10519327 | 11027426 | 547 | 630 | Change Order
2020 | Richmond Metropolitan Transportation Authority | Protective Coatings 2018 | Other | 9400000 | 6509460 | 543 | 620 | None
2020 | Richmond Metropolitan Transportation Authority | Miscellaneous Repairs - 2018 | Other | 3100000 | 2450996 | 321 | 429 | None
2020 | Rockingham County | Massanetta Springs Road Project | Design-Bid-Build | 3485250 | 2520525 | 250 | 268 | None. Timeline is in Days.
2020 | Rockingham County Public Schools | Fulks Run Elementary School - Renovation | Other | 5521427 | 5454636 | 330 | 270
2020 | Stafford County Public Schools | North Star-ECSE | Design-Bid-Build | 3452000 | 3283988 | 175 | 233 | There were punch list and close out issues and the contractor asked for additional days and general conditions and we settled on 11 days for an additional $28,776.29. That agreement was signed 07/23/2019
2020 | Stafford County Public Schools | AGWMS-GES Renovation | Design-Bid-Build | 3896059 | 3810811 | 487 | 486
2020 | Town of Christiansburg | Falling Branch Intersectin Improvements | Design-Bid-Build | 1842968 | 2050589 | 270 | 477 | no post closure issues. Project scope expanded from original due to unforeseen utility movement and cross walk
2020 | Town of Front Royal | Police Department Construction | Design-Bid-Build | 9000000 | 8719314 | 450 | 1410 | Architectural deficiencies Weather delays Network Cables Painted Settlement of Claims, Project Closeout issues
2020 | Town of South Hill | US Route 1 at Route 138 Intersection Improvements | Other | 2227194 | 2205847 | 250 | 415
2020 | Virginia Community College System - System Office | BRCC - New Const - Construct Parking Garage | Design-Bid-Build | 4581224 | 4603105 | 275 | 296
2020 | Virginia Community College System - System Office | JSRCC- DowntownImprovements to Phase I Facility - (CM) | Other | 5991880 | 4849431 | 690 | 1171
2020 | Virginia Community College System - System Office | PDCCC - Major Mechanical Renovation, Hobbs Campus | Other | 3065538 | 2962538 | 270 | 617
2020 | Virginia Community College System - System Office | Renovate Main Hall, Middletown Campus, Lord Fairfax | CM@Risk | 11824291 | 12514549 | 690 | 659
2020 | Virginia Polytechnic Institute and State University | Renovations for Undergraduate Science Laboratories | Design-Bid-Build | 6552944 | 5907114 | 360 | 360 | none
2020 | Virginia Polytechnic Institute and State University | Commonwealth Ballroom Improvements | Design-Bid-Build | 2202985 | 2197871 | 236 | 251 | none
2020 | Western Virginia Water Authority | Carvins Cove Filter | Design-Bid-Build | 3845809 | 3584576 | 300 | 300 | None
2020 | Wythe County Public Schools | George Wythe High School Renovation and Addition | Design-Bid-Build | 12250000 | 12738849 | 540 | 630
2019 | Albemarle County | Woodbrook E.S. Additions and Renovations | Design-Bid-Build | 17531381 | 16707272 | 422 | 438 | None
2019 | Albemarle County | Henley Middle School Addition and Renovations | Design-Bid-Build | 2598640 | 2590999 | 207 | 374 | HVAC issue currently under correction
2019 | Albemarle County | Hydraulic Road/Barracks Road Sidewalks | Design-Bid-Build | 2531036 | 2528338 | 137 | 169 | None
2019 | Arlington County Government | Four Mile Run Sanitary Sewer Relief Line Relining | Other | 2322870 | 2262120 | 180 | 120 | After project complete, damage to a newly relined 48" Sanitary Sewer (below this project's location) was discovered. Communicating with insurance and other entities to resolve.
2019 | Arlington County Government | Washington Blvd Bike Trail Construction | Other | 2112709 | 2140307 | 365 | 291
2019 | Bedford County Public Schools | New Liberty Middle School | Design-Bid-Build | 35884233 | 35135750 | 620 | 620
2019 | Bedford County Public Schools | New Gym at Liberty High School | Design-Bid-Build | 5615997 | 5487982 | 434 | 434
2019 | Charlottesville City | CONSTRUCTION OF LIGHTED SKATE PARK | Design-Bid-Build | 2019493 | 2094991 | 235 | 243 | none
2019 | City of Newport News | Operations Warehouse | Design-Bid-Build | 2276000 | 2066233 | 240 | 298 | None
2019 | City of Staunton | Johnson Street and New Street Parking Garage Repairs | Design-Bid-Build | 1698952 | 2045266 | 365 | 365
2019 | County of Accomack | Invitation for Bids #709 - Runway 3- 21 Pavement Rehabilitation & Runway Lighting Rehabilitation | Design-Build | 4240000 | 3812281 | 60 | 59 | small section of concrete to be repaired after it raised.
2019 | County of Fairfax | Burkholder Building Renovations | Other | 3265000 | 3257205 | 250 | 290 | NA
2019 | County of Fairfax | Pohick Creek at Queen Victoria | Design-Bid-Build | 2177561 | 2374329 | 479 | 401 | NA
2019 | County of Fairfax | Pohick Creek at Greentree Village | Design-Bid-Build | 2589872 | 2271611 | 419 | 435 | NA
2019 | County of Fairfax | Dead Run Stream Restoration | Design-Bid-Build | 2295000 | 2390271 | 381 | 372 | NA
2019 | County of Loudoun | Interior Buildout for 742 Miller Drive | Design-Bid-Build | 2099000 | 2158543 | 110 | 141 | None
2019 | Department of Forestry | JUDGE MATTHEWS AND ALICE HOUSE: RENOVATIONS | Design-Bid-Build | 2627097 | 2450000 | 365 | 380 | No major issues
2019 | Fort Monroe Authority | Renovation of Building 96 for DGS | Design-Bid-Build | 2350000 | 2752382 | 172 | 284 | Still trying to get complete as-builts and close-out documents.
2019 | Hampton Roads Sanitation District | Lucas Creek - Woodhaven IFM Replacement Phase I | Design-Bid-Build | 2655506 | 2622283 | 300 | 411 | Final change order has been slow to resolve.
2019 | Henrico County Government | High School Athletic Field Improvements | Design-Bid-Build |  | 5727670 | 243 | 303 | None
2019 | Henrico County Government | Human Services Ground Floor Renovation Project | Design-Bid-Build | 2180824 | 1925323 | 210 | 250 | None
2019 | Henrico County Government | Henrico Area Mental Health & Developmental Services East Clinic | Design-Bid-Build | 8798938 | 7180033 | 377 | 377 | None
2019 | Henrico County Government | High School Athletic Field Improvements – Phase 2 | Design-Bid-Build |  | 2143582 | 243 | 243 | None
2019 | James Madison University | CONSTRUCT WEST CAMPUS PARKING DECK | Design-Build | 11498000 | 11789957 | 473 | 386 | Landscaping Lighting Adding Electric Spaces
2019 | Newport News Public Schools | Hines Elementary School HVAC R2 | Design-Bid-Build | 2295000 | 2295000 | 488 | 380 | None
2019 | Newport News Public Schools | Lee Hall Elementary School HVAC R2 | Design-Bid-Build | 2584934 | 2584934 | 457 | 522 | Had to construct one (1) hour fire rated wall around mechanical room.
2019 | NRV Regional Water Authority | Prices Fork Pump Station and Water Transmission Main | Design-Bid-Build | 3093900 | 4102785 | 300 | 616 | N/A
2019 | Town of Luray | West Main Street Bridge | Design-Build | 3856020 | 4124142 | 385 | 415 | Two minor construction repairs
2018 | City of Covington | Peter's Mountain Landfill | Design-Bid-Build | 2390500 | 2307347 | 120 | 90
|  |  | TOTAL | 2568775067 | 2555644271
| - |  |  | Budget by method | Actual by method | Difference by method | % of total | Average $ over/under budget
|  |  | Design-Bid-Build | 1627557749 | 1660300912 | 32743163 | 63.36% | 142983.2445
|  |  | Design-Build | 83935668 | 81216271 | -2719397 | 3.268% | -247217.9091
|  |  | CM@Risk | 589554861 | 547432901 | -42121960 | 22.95% | -1914634.5455
|  |  | Other | 267726789 | 266694187 | -1032602 | 10.42% | -27173.7368
|  |  | TOTAL | 2568775067 | 2555644271 | -13130796
|  |  |  | Count | Percentage | Average Project cost
|  |  | Design-Bid-Build | 229 | 76.33% | 7107239.0786
|  |  | Design-Build | 11 | 3.667% | 7630515.2727
|  |  | CM@Risk | 22 | 7.333% | 26797948.2273
|  |  | Other | 38 | 12.67% | 7045441.8158
|  |  | TOTAL | 300
|  |  |  | Hard bid | Alternative
|  |  | Design-Bid-Build | 1627557749
|  |  | Design-Build |  | 83935668
|  |  | CM@Risk |  | 589554861
|  |  | Other |  | 267726789
|  |  |  | Hard bid | Alternative
|  |  | Design-Bid-Build | 229
|  |  | Design-Build |  | 11
|  |  | CM@Risk |  | 22
|  |  | Other |  | 38

## $5M or more
Year | Agency Name | Project | Construction Method | Budget | Actual | Timeline | Actual | Comments
2021 | City of Harrisonburg | Project #256.2B Eastern City Limits to Port Republic Road (City Contract 2019019-PU-B) | Design-Bid-Build | 5000000 | 2522128 | 560 | 820 | None reported in the procurement file ITB 2019019-PU-B Notice to Proceed: 09/16/2019 Completion Date: 12/08/21 Final Payment Amount: $2,522,127.56
2021 | City of Williamsburg | Monticello Ave PPTA | Design-Build | 5000000 | 3850113 | 334 | 632 | Long Completion date was due to material availability, weather along with Covid19 delays.
2020 | Henrico County Government | Glen Allen Elementary School Addition | Design-Bid-Build | 5010139 | 4875127 | 699 | 701 | None
2020 | County of Fairfax | DVS – West Ox Facility | Design-Bid-Build | 5109756 | 5538471 | 545 | 660 | NA
2020 | Chesterfield County | Robious Road Widening – Powhatan County Line to Robious Forest Way | Design-Bid-Build | 5175000 | 4635711 | 204 | 371 | None
2020 | Western Virginia Water Authority | Summit View Sewer | Design-Bid-Build | 5207217 | 3758862 | 210 | 336 | none
2020 | Rockingham County | Port Road Emergency Response Station | Design-Bid-Build | 5277000 | 5396912 | 18 | 18 | None
2020 | City of Virginia Beach | Royal Palm Arch Sanitary Sewer Rehab | Design-Bid-Build | 5300000 | 5536819 | 450 | 582 | N/A
2020 | Charlottesville City | INVITATION FOR BID # CIRCUIT COURTHOUSE RENOVATION & ADDITION/18-26 | Design-Bid-Build | 5332994 | 4113326 | 403 | 1029 | Very slow performance of contractor in remedying punchlist items. Plumbing issues which required corrective action. Electrical issues (lighting) which required corrective action.
2020 | James Madison University | Jackson Hall Renovation | Design-Bid-Build | 5497000 | 6164000 | 407 | 408 | Covid; building wasn't able to be fully occupied until almost summer of 2021.
2020 | Rockingham County Public Schools | Fulks Run Elementary School - Renovation | Other | 5521427 | 5454636 | 330 | 270
2020 | Roanoke City Government | Fire Station 7 Memorial | Other | 5570000 | 6021345 | 420 | 545 | None provided
2020 | County of Loudoun | Construction of the DC United Stadium Site | Design-Bid-Build | 5573333 | 7626449 | 473 | 548 | Warranty issues related to landscaping and a delay in a bus shelter drip edge. However, all issues have been resolved.
2020 | Bedford County Public Schools | New Gym at Liberty High School | Design-Bid-Build | 5615997 | 5487982 | 434 | 434
2020 | City of Virginia Beach | North Lake Holly Watershed Improvements | Design-Bid-Build | 5814176 | 4612895 | 548 | 715
2020 | County of Fairfax | Old Courthouse Spring Branch Valley Park | Design-Bid-Build | 5886798 | 6140875 | 450 | 459
2020 | County of Fairfax | Reston Community Center Aquatics | Design-Bid-Build | 5922000 | 5481320 | 305 | 315 | NA
2020 | Chesterfield County Public Schools | Construction, Falling Creek Middle School Improvements | Design-Bid-Build | 5959801 | 3450457 | 118 | 420 | None
2020 | Virginia Community College System - System Office | JSRCC- DowntownImprovements to Phase I Facility - (CM) | Other | 5991880 | 4849431 | 690 | 1171
2020 | Arlington County Government |  | Design-Bid-Build | 6080941 | 5945562 | 270 | 722 | N/A
2020 | Chesterfield County | Fire Station #25 | Design-Bid-Build | 6149804 | 6410057 | 495 | 510 | Yes
2020 | County of York | CONSTRUCTION OF FIRE STATION #1 (GRAFTON AREA) | Design-Bid-Build | 6197980 | 6636484 | 395 | 513 | DRAINAGE IMPROVEMENT PROJECT (IFB Y-10157-FS), AWARDED TO WALTER C VIA. FOR $26,900.00 THE PROCUREMENT METHOD FOR THE CONSTRUCTION OF FIRE STATION #1 WAS DONE THROUGH AN INVITATION FOR BIDS (IFB# 2075 - WHICH WAS POSTED ON EVA ON 1/3/2018)
2020 | Arlington Public Schools | Randolph Elementary School HVAC Improvement Project | Design-Bid-Build | 6200000 | 5136445 | 441 | 468 | Construction commenced June 22, 2018. Warranty period expired October 3, 2020. The budget information provided for the two projects includes both construction costs and soft costs.
2020 | City of Winchester | Woodstock Lane Infrastructure Improvements | Other | 6200000 | 6035963 | 365 | 365
2020 | University of Virginia | Main Heating Plant Boiler #6 | CM@Risk | 6400000 | 7285505 | 670 | 837 | Approved - also confirmed by Martin West and Jenn Glassman here at UVA
2020 | County of York | CONSTRUCTION, FIRE STATION | Design-Bid-Build | 6500000 | 6636484 | 441 | 539
2020 | Virginia Polytechnic Institute and State University | Renovations for Undergraduate Science Laboratories | Design-Bid-Build | 6552944 | 5907114 | 360 | 360 | none
2020 | Loudoun County Public Schools | Entry Modifications for 24 ES and MS (group 2a and 2B- (GMP 2 under CMaR contract 18-474) | CM@Risk | 6713879 | 4008476 | 334 | 516 | None
2020 | County of York | HVAC REPLACEMENT, METAL ROOF & EXTERIOR WINDOWS AND DOORS | Design-Bid-Build | 6804231 | 7254875 | 548 | 820
2020 | Hampton Roads Sanitation District | Boat Harbor Treatment Plant Switchgear & Controls | Design-Bid-Build | 6893065 | 6821171 | 580 | 580 | None
2020 | Albemarle County | Hollymead Dam Spillway Improvement | Design-Bid-Build | 6910200 | 6927836 | 571 | 1407
2020 | County of Fairfax | Hayfield Road Pipe Conveyance System | Design-Bid-Build | 6956900 | 7146984 | 420 | 355
2020 | Hanover County | Sliding Hill road | Design-Build | 7000000 | 6836855 | 487 | 438
2020 | University of Virginia | 652 Peter Jefferson Parkway, 2nd Floor Renovation - Breast Care Center | Design-Bid-Build | 7000000 | 4284848 | 301 | 997 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center - A246 College at Wise. This report is for A209 Medical Center
2020 | Spotsylvania County | Animal Shelter Expansion, Renovation | Other | 7002486 | 7069945 | 780 | 977 | none
2020 | City of Lynchburg | MAIN STREET BRIDGE | Design-Bid-Build | 7131385 | 7008357 | 450 | 540 | NONE
2020 | Hampton Roads Sanitation District | Manhole & Siphon Rehab - North Shore System | Design-Bid-Build | 7260921 | 6905511 | 490 | 760 | Extended warranty on certain items.
2020 | Henrico County Government | High School Athletic Field Improvements - Phase 3 (Deep Run, Glen Allen, and Godwin High Schools) | Design-Bid-Build | 7500000 | 7263059 | 250 | 300 | n/a
2020 | Hampton Roads Sanitation District | Orcutt Ave & Mercury Blvd GS Improvements | Design-Bid-Build | 7763168 | 7600000 | 554 | 584 | None
2020 | City of Chesapeake | Centerville Rehabilitation | Design-Bid-Build | 7793596 | 7911739 | 9 | 9 | NONE
2020 | University of Virginia | ECCCC 4th Floor Fit Out | CM@Risk | 7950000 | 10488253 | 780 | 1647 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center - A246 College at Wise. This report is for A209 Medical Center
2020 | City of Chesapeake | Centerville Turnpike Bridge Rehab | Design-Bid-Build | 8100000 | 7992721 | 515 | 508 | Procurement Method : Other -- Invitation for Bids (IFB)
2020 | Harrisonburg- Rockingham Regional Sewer Authority | Blacks Run Interceptor Improvements | Design-Bid-Build | 8210000 | 6537674 | 550 | 469
2020 | City of Virginia Beach | Indian River Road & Kempsville Road Intersection Improvements | Design-Bid-Build | 8337746 | 11022818 | 640 | 575
2020 | University of Virginia | Athletics Complex Phase 1 Early Site Package | Design-Bid-Build | 8400000 | 11871111 | 242 | 847 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2020 | Henrico County Government | Meredith Branch Force Main | Design-Bid-Build | 8500000 | 706382 | 730 | 1308 | Late completion
2020 | Shenandoah County | Sheriff's Office | Design-Bid-Build | 8500000 | 9678345 | 7302020 | 11302020 | n/a
2020 | Longwood University | Construct Admissions Office | Design-Bid-Build | 8561000 | 7858846 | 450 | 614 | project closeout issues
2020 | Henrico County Government | Henrico Area Mental Health & Developmental Services East Clinic | Design-Bid-Build | 8798938 | 7180033 | 377 | 377 | None
2020 | County of Fairfax | Bailey's Shelter & Supportive Housing | Design-Bid-Build | 8843000 | 9272447 | 518 | 599
2020 | Town of Front Royal | Police Department Construction | Design-Bid-Build | 9000000 | 8719314 | 450 | 1410 | Architectural deficiencies Weather delays Network Cables Painted Settlement of Claims, Project Closeout issues
2020 | City of Virginia Beach | Police 4th Precinct Bldg | Design-Bid-Build | 9051779 | 7103996 | 405 | 624 | N/A
2020 | NRV Regional Water Authority | Plum Creek Transmission Main Phase 1 and Phase 2 | Design-Bid-Build | 9168000 | 9892500 | 595 | 585 | None
2020 | Henrico County Government | Crestview Elementary School Renovations | Design-Bid-Build | 9283941 | 8425497 | 484 | 736 | None
2020 | Richmond Metropolitan Transportation Authority | Protective Coatings 2018 | Other | 9400000 | 6509460 | 543 | 620 | None
2020 | University of Virginia | University Hall (U- Hall) Abatement & Demolition | Design-Build | 9800000 | 6518658 | 289 | 1010 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2020 | County of Fairfax | Woodlawn Fire Station | Design-Bid-Build | 9933000 | 9492613 | 644 | 531 | NA
2020 | Virginia Port Authority | Dredging IFB - Public Opening | Design-Bid-Build | 10190110 | 9534520 | 532 | 532 | Sealed Competitive Bidding via an IFB
2020 | City of Virginia Beach | South Lake Holly Watershed Improvements | Design-Bid-Build | 10260485 | 9039817 | 913 | 1066
2020 | Capital Region Airport Commission | Cargo Apron Eastside | Design-Bid-Build | 10500000 | 8838853 | 270 | 270 | none
2020 | Prince William County Service Authority | Colchester Interceptor and Pump Station | Other | 10519327 | 11027426 | 547 | 630 | Change Order
2020 | Stafford County Public Schools | Energy Performance Contract for Stafford County Public Schools | Other | 10650651 | 10650651 | 995 | 1025
2020 | Arlington Public Schools | Gunston Middle School HVAC Improvement Project | Design-Bid-Build | 10655000 | 8723689 | 442 | 467 | Construction commenced June 21, 2018. Warranty period expired October 15, 2020. The budget information provided for the two projects includes both construction costs and soft costs.
2020 | Roanoke City Government | E911 VA 811 Facility | Other | 10741087 | 11160233 |  |  | None provided
2020 | Chesterfield County Public Schools | Matoaca Middle School Addition | Design-Bid-Build | 10786253 | 10583541 | 385 | 377
2020 | County of Loudoun | Construction of the Lovettesville Community Center | Design-Bid-Build | 10808400 | 1283305 | 912 | 193 | Terminated for convenience after phase 1 completed
2020 | Henrico County Government | Pemberton Elementary School Renovation | Design-Bid-Build | 10829171 | 10131210 | 699 | 824 | None
2020 | Henrico County Government | Chamberlayne Elementary School Renovations | Design-Bid-Build | 10892301 | 8270524 | 738 | 858 | None
2020 | Harrisonburg- Rockingham Regional Sewer Authority | Enhanced Biosolids Reuse and Reduction Project | Design-Bid-Build | 11222933 | 11320842 | 600 | 644 | None
2020 | James Madison University | CONSTRUCT WEST CAMPUS PARKING DECK | Design-Build | 11498000 | 11789957 | 473 | 386 | Landscaping Lighting Adding Electric Spaces
2020 | University of Virginia | Carr's Hill Renovation | CM@Risk | 11700000 | 1036433 | 537 | 1393 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2020 | Virginia Community College System - System Office | Renovate Main Hall, Middletown Campus, Lord Fairfax | CM@Risk | 11824291 | 12514549 | 690 | 659
2020 | County of Fairfax | Murraygate Village Apartments | Design-Bid-Build | 11973575 | 15440928 | 571 | 749 | NA
2020 | Wythe County Public Schools | George Wythe High School Renovation and Addition | Design-Bid-Build | 12250000 | 12738849 | 540 | 630
2020 | University of Virginia | New Softball Stadium | CM@Risk | 13000000 | 19641061 | 528 | 1409 | The University of Virginia is comprised of (3) three agencies: - A207 Academic - A209 Medical Center- A246 College at Wise. This is or A207 Academic
2020 | Henry County | Philpott Water Filtration Plant Upgrade to 6.0 MGD | Design-Bid-Build | 13626557 | 13626557 | 730 | 1095 | One of the raw water pumps and finished water pumps having issues.
2020 | Hampton Roads Sanitation District | Williamsburg Treatment Plant Generator & Switchgear Replacement | Design-Bid-Build | 13992672 | 14115477 | 690 | 698 | None
2020 | Rockingham County Public Schools | John C. Myers Elementary School | Other | 14110630 | 13610153 | 536 | 596
2020 | Galax City Public Schools | Galax Elementary School Renovation Project | Design-Bid-Build | 15552000 | 1710000 | 973 | 1187 | None
2020 | City of Virginia Beach | South Lake Holly Section IV | Design-Bid-Build | 16009587 | 15681839 | 913 | 1066 | N/A
2020 | Longwood University | New Academic Building | Design-Bid-Build | 16115400 | 16530511 | 630 | 1425 | Non
2020 | Fairfax County Schools | Mount Vernon Woods Elementary School Renovation | Design-Bid-Build | 16750000 | 17044085 | 851 | 1216 | NA
2020 | County of Fairfax | Solids Processing Rehabilitation, Phase II | Design-Bid-Build | 16750000 | 18433980 | 915 | 844
2020 | Prince William County | Construction of Fire and Rescue Station 22 | Design-Bid-Build | 16970713 | 16766731 | 112020 | 42022 | Occupancy December 2020, Project Closeout Completed April 2022
2020 | Virginia Polytechnic Institute and State University | Student Athlete Performance Center | Design-Bid-Build | 17059490 | 16763923 | 487 | 487
2020 | Virginia Polytechnic Institute and State University | Student Athlete Performance Center | Design-Bid-Build | 17059490 | 16763923 | 450 | 450 | none
2020 | Albemarle County | Woodbrook E.S. Additions and Renovations | Design-Bid-Build | 17531381 | 16707272 | 422 | 438 | None
2020 | University of Mary Washington | Renovate Residence Halls - Phase II (Virginia Hall) | CM@Risk | 17901616 | 19041679 | 343 | 357
2020 | County of Loudoun | Construction of the New Loudoun County Animal Services Facility | Design-Bid-Build | 17975850 | 18311445 | 540 | 791 | none
2020 | University of Mary Washington | Improvements - Renovate Residence Halls (Willard Hall Renovation) | CM@Risk | 18400780 | 19311522 | 286 | 376
2020 | County of Fairfax | Massey Demo | Design-Bid-Build | 18682000 | 6941108 | 615 | 689 | NA
2020 | Fairfax County Schools | Silverbrook Elementary School Renovation | Design-Bid-Build | 19994000 | 20032321 | 615 | 980 | NA
2020 | James Madison University | Wilson Hall Renovation | CM@Risk | 20008990 | 20186612 | 378 | 366
2020 | County of Loudoun | Construction of the Public Safety Firing Range | Design-Bid-Build | 20398000 | 21360506 | 460 | 658 | none
2019 | Fairfax County Schools | Belle View Elementary School Renovation | Design-Bid-Build | 20790000 | 20957526 | 791 | 1156 | NA
2019 | City of Newport News | Parking Garage, City Center, Phase Four | Other | 21593000 | 22531879 | 503 | 595
2019 | Henrico County Government | Tuckahoe Middle School Renovation | Design-Bid-Build | 22632393 | 27796552 | 700 | 777 | None
2019 | Radford University | Renovate Curie and Reed Halls | CM@Risk | 22708530 | 22706892 | 602 | 1080
2019 | City of Fairfax | Northfax Intersection & Drainage Improvement Project | Other | 23848500 | 23848500 | 730 | 730 | Traffic signal was damaged in vehicular accident before punch list was completed.
2019 | Greene County Public Schools | L618GCPS - DEB_CCP_William Monroe Middle and High School Rennovation | CM@Risk | 23975800 | 24489225 | 532 | 868 | Slope issues on the loading dock at the Middle School. Repaired by contractor. Drain line issues at the MS causing back up in cafeteria and restrooms. Had to pull up a section of terrazzo and slab to repair.
2019 | Chesterfield County Public Schools | Crestwood Elementary School Construction | Design-Bid-Build | 24178807 | 24219539 | 660 | 660
2019 | Chesterfield County Public Schools | Matoaca Elementary School Construction | Design-Bid-Build | 24861832 | 25140543 | 477 | 478
2019 | James Madison University | Phillips Dining Hall | CM@Risk | 25112184 | 25826276 | 542 | 595 | Extensive Contractor delays and quality issues.
2019 | City of Virginia Beach | North Lake Holly Section IIIA | Design-Bid-Build | 25351135 | 27874216 | 548 | 711 | N/A
2019 | Chesapeake Bay Bridge and Tunnel District | Mill and Repave Trestles, Replace End Dams | Design-Bid-Build | 27000000 | 26721706 | 343 | 724 | No
2019 | Frederick County Public Schools | 12th Elementary School Construction | Design-Bid-Build | 28500000 | 27227401 | 731 | 520 | commissioning issues on lighting
2019 | Hampton Roads Sanitation District | Providence Road Offline Storage Facility | Design-Build | 29953000 | 31131582 | 855 | 881 | None
2019 | Hampton Roads Sanitation District | Pressure Reducing Station Reliability Upgrades | CM@Risk | 33282000 | 30454524 | 1135 | 1135 | None
2019 | James Madison University | East Campus Parking Deck | CM@Risk | 34676293 | 35369303 | 1039 | 521
2019 | Bedford County Public Schools | New Liberty Middle School | Design-Bid-Build | 35884233 | 35135750 | 620 | 620
2019 | City of Newport News | SCOT Center PPEA | CM@Risk | 38811692 | 39348167 | 412 | 576 | Project indicated as Other were issued as Invitation for Bids.
2019 | Chesterfield County Public Schools | Manchester Middle School Construction | Design-Bid-Build | 41283593 | 41283593 | 857 | 857
2019 | City of Staunton | STAUNTON HIGH School additions and renovations | Design-Bid-Build | 43130335 | 44041818 | 639 | 640 | MAIN AND AUX gym flooring issues to be resolved
2019 | James Madison University | East Campus Student Housing | CM@Risk | 47850000 | 49503462 | 414 | 504 | Tremendous workmanship and system errors from Contractor.
2019 | County of Fairfax | Innovation Center Station Parking Garage | Design-Bid-Build | 51639920 | 49512692 | 700 | 850 | NA
2019 | Old Dominion University | SB Ballard Stadium Renovations | CM@Risk | 53653240 | 5960724 | 445 | 445 | Warranty
2019 | Prince William County Schools | Potomac Shores Middle School | Design-Bid-Build | 54104420 | 52542298 | 867 | 929 | None
2019 | City of Virginia Beach | Virginia Beach Sports Center | Other | 65804076 | 65365758 | 863 | 820
2019 | James Madison University | Construct New College of Business | CM@Risk | 70822168 | 72641206 | 1106 | 1078
2019 | Loudoun County Public Schools | Lightridge High Schools (HS-9) new construction | Design-Bid-Build | 110399300 | 114043778 | 699 | 973 | None
2019 | James Madison University | New Construction Convocation Hall | CM@Risk | 113900000 | 115675841 | 938 | 907
|  |  | TOTAL | 2037550613 | 1939837580
| - |  |  | Budget by method | Actual by method | Difference by method | % of total | Average $ over/under budget
|  |  | Design-Bid-Build | 1198655086 | 1150085325 | -48569761 | 58.83% | -578211.4405
|  |  | Design-Build | 63251000 | 60127165 | -3123835 | 3.104% | -624767
|  |  | CM@Risk | 578691463 | 535489710 | -43201753 | 28.4% | -2273776.4737
|  |  | Other | 196953064 | 194135380 | -2817684 | 9.666% | -216744.9231
|  |  | TOTAL | 2037550613 | 1939837580 | -97713033
|  |  |  | Count | Percentage | Average Project cost
|  |  | Design-Bid-Build | 84 | 69.42% | 14269703.4048
|  |  | Design-Build | 5 | 4.132% | 12650200
|  |  | CM@Risk | 19 | 15.7% | 30457445.4211
|  |  | Other | 13 | 10.74% | 15150235.6923
|  |  | TOTAL | 121
|  |  |  | Hard bid | Alternative
|  |  | Design-Bid-Build | 1198655086
|  |  | Design-Build |  | 63251000
|  |  | CM@Risk |  | 578691463
|  |  | Other |  | 196953064
|  |  |  | Hard bid | Alternative
|  |  | Design-Bid-Build | 84
|  |  | Design-Build |  | 5
|  |  | CM@Risk |  | 19
|  |  | Other |  | 13